CONTROLLED MARKETING PROGRAM Event & Community Outreach Program Chamber Engagement, Sponsorship, Volunteer and Hosted-Event Control Document ID: MKT-002 Author and Chief Editor: Matt Ramsey Final Approver: Jeremy Thamert, Owner Lifecycle: BETA - Draft for Final Approval Source schedule: MH Construction 2027 Field Marketing Calendar Issue date: August 4, 2026 Show up. Serve well. Build legitimate relationships. Follow through.

Control: Version 1.0 | Status Draft | Author and Chief Editor: Matt Ramsey | Co-Editor: Todd Shoeff | Final Approver: Jeremy Thamert

# Document Control

| Control | Value |
| --- | --- |
| Document ID | MKT-002 |
| Canonical filename | mh-event-and-community-outreach-program |
| Department | Marketing Department |
| Author / Chief Editor | Matt Ramsey |
| Final Approver | Jeremy Thamert, Owner |
| Lifecycle | BETA - Draft for Final Approval |
| Accountable position | CHNAV / Business Development Command |
| Responsible position | Marketing Lead |
| System of action | Marketing Flight |
| Authoritative final archive | Dedicated in-house server |
| Source planning register | MH Construction 2027 Field Marketing Calendar |
| Review cadence | Monthly during 2027 beta; formal AAR after Q2 and year-end |

# 1. Command Intent

MHC will build durable, legitimate local relationships by consistently attending, sponsoring, volunteering at and hosting selected chamber, industry and community events. The program converts event presence into service, trust, market intelligence, qualified relationships and accountable follow-through. It is a BETA operating program and may scale, contract or change after measured reviews.

## Ethical engagement rule

“Infiltrate” is treated only as internal campaign shorthand for sustained, transparent participation. MHC personnel must identify their affiliation, follow organizer rules, avoid deceptive access, improper influence, quid pro quo, concealed political activity and misuse of confidential information. Chamber leadership or committee service must benefit the organization and community, not create a hidden purchasing advantage.

# 2. Scope and Objectives

Create a deliberate presence in selected Chambers of Commerce and civic networks.

Earn trust by contributing time, expertise, sponsorship and hosted value.

Build relationships with Client Partners, Trade Partners, public agencies, workforce partners, veterans and community leaders.

Capture event-generated contacts and opportunities in Marketing Flight.

Create approved public content that supports the MH veteran-owned and community-service brand.

Develop a repeatable annual portfolio that can scale without overloading operations or diluting follow-through.

# 3. Authority and Role Matrix

| Position | Program responsibility |
| --- | --- |
| Owner / Final Approver | Final approval for program, annual plan, hosted events and controlled publications. |
| Upper Brass | Controlled roster: CEO, COO, CHENG, CHNAV and Owners. Members serve as chamber relationship owners and Event Sponsors. |
| CHNAV / Business Development Command | Accountable position for outreach strategy, chamber relationship plan, opportunity handoff and portfolio value. |
| Marketing Lead | Responsible for calendar, event research, Marketing Flight records, briefs, content, follow-up and reporting. |
| Upper Brass Event Sponsor | Assigned executive position who represents MHC, owns priority relationships and completes required follow-up. |
| Chief Editor | Controls program architecture, terminology, brand alignment and document integrity. |
| IT Specialist | Controls Marketing Flight access, server archive, integrations, backup and recovery. |
| CFO / Financial Lead | Controls budget coding, commitments, reconciliation, tax documentation and financial records. |
| Safety and Systems Command | Reviews volunteer, booth, vehicle, equipment, food, alcohol and public-event safety requirements. |
| Project Manager / Superintendent | Verifies project facts, staffing impacts and client/site permissions when event content involves a project. |

Upper Brass is the controlled position grouping of CEO, COO, CHENG, CHNAV and Owners. Each activated event receives a primary Event Sponsor and backup. The annual calendar allocates attendance so executive participation remains deliberate and does not interfere with project delivery.

## 3.1 Target Chamber Campaign

| Priority | Target | 2027 command objective |
| --- | --- | --- |
| 1 | Tri-City Regional Chamber | Prestige objective and long-range priority. Build consistent access, earn committee responsibility and prepare for future board eligibility without forcing the timeline. |
| 2 | Richland Chamber | Active penetration objective. Maintain Cool Desert Nights Committee performance and secure an MHC board seat when the Chamber completes its process. |
| 3 | Pasco Chamber | Agriculture objective. Use only the supplied calendar events and approved Chamber relationships to establish credible agriculture-sector access. |
| 4 | West Richland Area Chamber | Veteran objective. Sponsor, volunteer and participate through the selected Veterans Day Parade schedule entry. |
| 5 | Tri-Cities Hispanic Chamber / Hispanic Heritage network | Relationship-development objective. Begin with listening and service through the supplied schedule; do not add or substitute events without discussion. |

# 4. Engagement Lanes

| Lane | Purpose | Control |
| --- | --- | --- |
| Attend | Observe, learn, build legitimate relationships and record opportunities. | No passive attendance without an assigned objective, contact target and follow-up owner. |
| Sponsor | Exchange approved value for defined visibility, access or community benefit. | Require written benefits, cost, audience, conflicts check, approval and fulfillment evidence. |
| Volunteer | Provide labor, expertise or service that benefits the organizer and community. | Require scope, supervision, safety, insurance, youth/vulnerable-person and media review. |
| Host | Create an MHC-controlled forum such as a briefing, roundtable, open house, service day or veteran/community event. | Require charter, budget, venue, permits, safety plan, guest controls, content plan and closeout. |

# 5. Research Library and Operating Calendar

The 100-event workbook remains the research library and evidence source. The executable 2027 calendar is condensed to 30 activations, normally two per month with three during selected strategic months. The operating calendar stays inside the Tri-Cities whenever practical and uses limited major-event exceptions. No research-library event is presented as an operating commitment unless it appears in the approved condensed calendar.

| Criterion | Weight | Decision test |
| --- | --- | --- |
| Strategic alignment | 20 | Supports chambers, construction, workforce, veterans, Client Partners or target markets. |
| Relationship value | 20 | Creates legitimate access to decision-makers, partners or community leaders. |
| Audience fit | 15 | Attendees match approved client, workforce, trade, public or referral segments. |
| Community value | 15 | Produces a defined public, charitable, workforce or economic-development benefit. |
| Activation quality | 10 | MHC can attend, sponsor, volunteer or host with a clear mission and deliverable. |
| Timing and capacity | 10 | Staffing, travel, project workload and lead time are workable. |
| Cost and measurable value | 5 | Cost is known and proportionate to objectives and expected evidence. |
| Risk and evidence readiness | 5 | Organizer, claims, permissions, safety, reputation and source evidence pass review. |

## Default BETA resource levels

| Score | Default resource assignment |
| --- | --- |
| 80-100 | Strategic anchor: assign Upper Brass sponsor and annual relationship plan. |
| 65-79 | Standard activation: assign lane, staffing, budget and follow-up owner. |
| 50-64 | Scheduled support: attend, volunteer or participate using the calendar-defined mode. |
| Below 50 | Retain on the authorized schedule and use the lowest-risk, lowest-cost suitable mode pending discussion. |

## 5.1 Conservative Annual Investment Control

The BETA uses a $30,000 MHC-funded annual ceiling for the condensed operating calendar. Every monetary commitment must pass the score, approval and benefit controls. The range is grounded in current local examples from $400 memberships and $500 community sponsorships through $6,000 membership or agriculture packages and $10,000 exclusive sponsorships.

| Budget class | 2027 ceiling | Control |
| --- | --- | --- |
| Chamber memberships and leadership access | $8,000 | Supports up to five target relationships, including a Regional Chamber tier if approved. |
| Strategic event sponsorships | $10,000 | Reserve for scored Tier 1 and Tier 2 activations; no automatic renewals. |
| MHC-hosted flagship seed funding | $7,500 | Maximum MHC net exposure; external sponsors must fund at least 60% of direct event cost before launch. |
| Travel, materials and volunteer activation | $3,000 | Local travel, booth materials, PPE, service supplies and controlled hospitality. |
| Management reserve | $1,500 | Owner-controlled contingency; unused funds remain uncommitted. |
| Total MHC-funded annual ceiling | $30,000 | Gross ceiling before documented sponsor reimbursements or in-kind contributions. |

Single-event planning caps are $1,000 for routine support, $2,500 for standard sponsorship and $6,000 for a strategic anchor. Any single commitment above $2,500, every hosted event and every exception requires Owner approval.

# 6. Stage-Gate Workflow

| Gate | Required action | Retained evidence |
| --- | --- | --- |
| Discover | Log event, organizer, source, recurrence, geography and possible participation lane. | Marketing Flight opportunity record |
| Validate | Confirm date, source, organizer, cost, sponsorship inventory, audience and cancellation terms. | Validation record with source links |
| Score | Apply weighted score, select portfolio tier and state decision rationale. | Event scorecard |
| Authorize | Assign Event Sponsor, approve lane, budget, staffing, message and risk controls. | Approved event decision record |
| Brief | Issue mission, objectives, contacts, talking points, logistics, dress, media and follow-up plan. | Event briefing sheet |
| Execute | Represent MHC openly, follow rules, capture approved contacts and document commitments. | Attendance, contact and expense records |
| Follow through | Enter contacts within one business day; complete commitments and sales handoff. | Marketing Flight tasks and handoff record |
| AAR and close | Compare objective to result, reconcile cost, retain proof and set next-year recommendation. | After Action Review and archive package |

# 7. 2027 Condensed Operating Calendar

This review draft contains 30 proposed activations: 26 in the Tri-Cities area and four major-event exceptions. Pendleton Round-Up is retained as the principal out-of-area community exception. Spokane AGC/WSDOT and agriculture events support industry access; Umatilla County Fair supports the regional agriculture market. The West Richland Veterans Day Parade is included under the Chief Editor’s prior direction and is the only entry not reproduced from the supplied workbook.

| # | Month | Event | City / State | 2027 date / window | Status | Participation mode |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | January | Washington and Oregon Potato Conference | Kennewick, WA | January 25-28, 2027 | Confirmed | Attendee, Exhibitor, Sponsor |
| 2 | January | Tri-Cities Sportsmen Show | Pasco, WA | Not found | Forecast | Attendee |
| 3 | January | Save the Date! AGC-WSDOT Annual Meeting | Spokane, WA | Jan 7, 2027 | Confirmed | Participant |
| 4 | February | Regional Home & Garden Show | Pasco, WA | Not confirmed | Forecast | Exhibit/Sponsor |
| 5 | February | Spokane Ag Show | Spokane, WA | February 2-4, 2027 | Confirmed | Attendee, Exhibitor, Sponsor |
| 6 | March | Custer's Spring Arts & Crafts Show | Pasco, WA | March 19-21, 2027 | Confirmed | Attendee, Exhibitor |
| 7 | March | Economic Summit | Tri-Cities, WA | Unknown | Forecast | Attendee |
| 8 | April | Lakeside Gem & Mineral Show | Kennewick, WA | April 18-19, 2027 | Confirmed | Attendee, Exhibitor |
| 9 | April | Pasco Taco Crawl | Pasco, WA | Not found | Forecast | Attendee |
| 10 | May | Tri-City Construction Council Annual Scholarship Golf Tournament | Kennewick, WA | Not confirmed | Forecast | Attend/Sponsor |
| 11 | May | Pasco Cinco de Mayo Parade & Festival | Pasco, WA | Not confirmed | Forecast | Attend/Sponsor/Vendor |
| 12 | May | Pasco Farmers Market | Pasco, WA | Not confirmed | Forecast | Attend/Exhibit |
| 13 | June | Cool Desert Nights | Richland, WA | Not confirmed | Forecast | Attend/Exhibit/Sponsor |
| 14 | June | Tri-Cities Pride Festival | Pasco, WA | Not found | Forecast | Attendee, Exhibitor (fully booked for 2024), Volunteer (closed for 2024), Performer/Talent (fully booked for 2024) |
| 15 | July | 2024 Water Follies Apollo Columbia Cup & STCU Over-the-River Air Show | Kennewick/Pasco, WA | Not found | Forecast | Spectator, Pit Pass |
| 16 | July | Pasco Grand Old 4th of July Celebration | Pasco, WA | Not confirmed | Forecast | Attend/Sponsor |
| 17 | July | Art in the Park Festival | Richland, WA | Not confirmed | Forecast | Attend/Exhibit/Sponsor |
| 18 | August | Benton Franklin Fair and Horse Heaven Round Up | Kennewick, WA | Unknown | Forecast | Attendee/Vendor |
| 19 | August | Umatilla County Fair | Hermiston, OR | Not Published | Forecast | Spectator, Participant, Vendor |
| 20 | September | Pendleton Round-Up | Pendleton, OR | Not Published | Forecast | Spectator, Participant |
| 21 | September | Mayors' BBQ | Tri-Cities, WA | Unknown | Forecast | Attendee |
| 22 | September | Tri-Cities Parade of Homes | Tri-Cities, WA | Not confirmed | Forecast | Attend/Sponsor |
| 23 | October | Business Showcase | Tri-Cities, WA | Unknown | Forecast | Exhibitor/Attendee |
| 24 | October | Field of Screams | Richland, WA | Not found | Forecast | Attendee |
| 25 | November | Pacific Northwest Vegetable Association Conference | Kennewick, WA | Not Confirmed | Forecast | Attendee, Exhibitor, Sponsor |
| 26 | November | Tri-Cities Wine Festival | Kennewick, WA | Not found | Forecast | Attendee |
| 27 | November | West Richland Tri-Cities Regional Veterans Day Parade | West Richland, WA | November 2027 - revalidate | Previously directed strategic addition | Sponsor / volunteer / participate |
| 28 | December | Hometown Holiday Parade | Kennewick, WA | Not confirmed | Forecast | Attend/Sponsor |
| 29 | December | NW Hort Expo | Kennewick, WA | Not Confirmed | Forecast | Attendee, Exhibitor, Sponsor |
| 30 | December | Winter Wonderland | Richland, WA | December 1-31, 2027 (estimated) | Forecast | Attendee |

This calendar is a proposed condensation for Chief Editor approval. No further addition, deletion or substitution becomes controlled until discussed and approved.

# 8. Chamber Engagement Campaign

Establish one controlled relationship plan for each approved Chamber.

Assign an executive relationship owner and an operating coordinator.

Define target committees, leadership forums, ribbon cuttings, workforce programs and sponsorship opportunities.

Attend consistently enough to become useful and credible; avoid isolated “logo-only” sponsorships without a relationship objective.

Record introductions, commitments, community issues and next actions in Marketing Flight.

Complete a quarterly AAR on access, service delivered, opportunities, reputation and workload.

# 9. Event Briefing and Conduct

## Required briefing content

event mission and measurable objective

Event Sponsor, attendees, backup and organizer contact

priority people and approved conversation objectives

approved MHC description, proof points and prohibited claims

participation lane, dress, booth, signage, materials and accessibility

travel, schedule, check-in, parking, venue and weather plan

safety, insurance, alcohol, food, minors, vehicles, equipment and emergency controls

photo, media, testimonial and social-post permissions

contact capture, commitment log and follow-up owner

budget, cost code, receipts and closeout deadline

## Conduct standard

Represent MHC openly and professionally. Serve before selling. Do not pressure organizers, collect personal data without a legitimate purpose, make unapproved promises, discuss confidential project information, offer improper gifts, use political activity to obtain business, or publish people and property without approval.

# 10. Sponsorship, Volunteer and Hosted-Event Controls

## Sponsorship due diligence

Verify the legal organizer, benefits, exclusions, audience, payment terms, cancellation terms, insurance and deliverable dates.

Check conflicts with clients, public officials, competitors, political activity, restricted industries and project procurement.

Assign every contracted benefit, proof requirement and fulfillment owner.

Reconcile actual cost and value during the AAR; renewal is never automatic.

## Volunteer activation

Obtain written scope, supervisor, location, schedule and task restrictions.

Review workers compensation, general liability, auto, tools, PPE, food handling, youth/vulnerable-person contact and background-check requirements.

Use an attendance roster, incident process and volunteer-hours record.

Do not allow volunteer work to become unapproved construction, professional design or regulated work.

## MHC-hosted event

Issue a one-page event charter defining purpose, audience, owner, budget, success criteria and cancellation authority.

Approve venue, occupancy, permits, insurance, accessibility, security, parking, weather and emergency plan.

Control invitations, registration, privacy, photography, food, alcohol, speakers, sponsors and public-official participation.

Complete financial reconciliation, contact follow-up, media release and AAR before closeout.

# 11. Marketing Flight and Sales Handoff

Marketing Flight is the system of action for event opportunities, organizers, contacts, tasks, campaigns and attribution. The in-house server retains the final approved archive package. Contacts must be entered or synchronized within one business day and must carry source event, date, relationship owner, consent basis, next action and due date.

## Default handoff trigger

Until the Owner approves a different threshold, Marketing transfers an event-generated opportunity to CHNAV/Sales when a contact identifies a specific project or procurement need, confirms decision timing and agrees to direct follow-up. Marketing retains attribution visibility while Sales controls the pursuit record.

# 12. Media, Brand and Public Communication

Use the approved MH logo, colors, typography and veteran-owned language.

Obtain organizer and subject permissions before publication.

Verify licenses, awards, safety, capacity, project, client and community-impact claims against controlled evidence.

Do not publish live security, access, private attendee, youth, medical or proprietary information.

Route social posts, email blasts and event recaps through Marketing Flight approval and scheduling.

Archive final public assets and approval evidence on the in-house server.

# 13. Performance and AAR

| Measure | Definition | BETA control |
| --- | --- | --- |
| Portfolio discipline | Percent of activated events with approved scorecard and decision record | 100% |
| Relationship follow-through | Priority contacts with assigned next action within one business day | 95% or higher |
| Commitment closure | Promises, introductions and organizer deliverables closed by due date | 100% |
| Forecast validation | Forecast events revalidated before commitment | 100% |
| Community contribution | Volunteer hours, in-kind support and hosted-event benefit | Report actuals; target set annually |
| Qualified opportunity value | Marketing Flight opportunities attributable to events and accepted by Sales | Report count, value and conversion |
| Sponsorship fulfillment | Contracted benefits received and documented | 100% or exception logged |
| Brand and compliance | Unauthorized claims, posts, gifts, political activity or privacy violations | Zero |
| Portfolio learning | Activated events receiving an AAR and next-year recommendation | 100% |

## Combined 2027 program score

| Score element | Points | Evidence |
| --- | --- | --- |
| Strategic chamber progress | 25 | Board/committee progress, relationship plan execution and target-market access. |
| Relationship and follow-through | 20 | Priority contacts, completed commitments, next actions and Sales handoffs. |
| Community and veteran value | 20 | Volunteer hours, in-kind benefit, organizer outcomes and veteran/community contribution. |
| Qualified pipeline contribution | 15 | Accepted Marketing Flight opportunities, estimated value and conversion evidence. |
| Execution and brand control | 10 | Briefings, attendance, sponsor fulfillment, AARs and zero critical violations. |
| Financial stewardship | 10 | Budget variance, sponsor leverage, cost per qualified relationship and documented value. |

The year-end score governs 2028 disposition: 80-100 expands the program; 70-79 authorizes controlled expansion; 60-69 holds scale and requires a corrective plan; below 60 contracts or stops the program. Any critical legal, safety, ethics, privacy or financial-control violation prevents expansion regardless of the numeric score.

# 14. Required Forms and Records

| Record ID | Required record | Primary system |
| --- | --- | --- |
| MKT-FRM-010 | Event opportunity and validation record | Marketing Flight |
| MKT-FRM-011 | Event scorecard and decision record | Marketing Flight; approved PDF to server |
| MKT-FRM-012 | Event briefing sheet | Marketing Flight / Field Command Center as applicable |
| MKT-FRM-013 | Event contact and commitment log | Marketing Flight |
| MKT-FRM-014 | Sponsorship benefits and fulfillment tracker | Marketing Flight / Finance record |
| MKT-FRM-015 | Volunteer activation plan and roster | Marketing Flight / Safety record |
| MKT-FRM-016 | Hosted-event charter and risk review | Marketing Flight; approved PDF to server |
| MKT-FRM-017 | Event After Action Review | Marketing Flight; final PDF to server |
| MKT-FRM-018 | Annual outreach portfolio and budget register | Marketing Flight / Sage 100 reference |

# 15. Approved Direction Register

The Owner direction below closes the program-level gaps for target hierarchy, executive participation, investment, hosted-event funding and the 2028 scale decision. Event-specific dates, prices, sponsor inventory and risks remain subject to validation before commitment.

| Decision | Approved direction |
| --- | --- |
| Target hierarchy | Tri-City Regional, Richland, Pasco, West Richland, then Hispanic Heritage network. |
| Upper Brass | CEO, COO, CHENG, CHNAV and Owners. |
| Annual MHC ceiling | $30,000 with category controls and Owner-controlled reserve. |
| Hosted-event doctrine | Go BIG, or Go Home: one flagship with at least 60% external sponsor funding and no more than $7,500 MHC net exposure. |
| 2028 scale test | Combined 100-point score: 80+ expand, 70-79 controlled expansion, 60-69 revise and hold, below 60 contract or stop. |

# Appendix A. Minimum Event Decision Record

event name, organizer, jurisdiction and verified source

confirmed date or forecast window and revalidation date

engagement lane and weighted score

portfolio tier and written decision rationale

Event Sponsor, attendees, responsible position and backup

objective, target relationships and community benefit

cash, in-kind, travel and labor budget

risk, conflicts, insurance, permits, privacy and media controls

approval, conditions, decision date and cancellation authority

Marketing Flight record, server archive path and retention class

# Appendix B. After Action Review Questions

What was the approved mission and was it achieved?

What community value did MHC deliver?

Which relationships advanced and what is the next action?

What qualified opportunities were identified and handed off?

What commitments remain open?

What did MHC spend in cash, labor, travel and in-kind support?

Were sponsorship benefits delivered?

What safety, conduct, privacy, brand or reputation issues occurred?

Should MHC repeat, expand, change or stop this activation?

What must change in the calendar, score or briefing before the next event?

# Appendix C. Economic Planning Sources

These official public sources establish a local planning range only. They do not add events to the authorized schedule. The Marketing Lead must revalidate current prices, benefits, availability and terms before every commitment.

| Source | Published planning signal | URL |
| --- | --- | --- |
| Tri-City Regional Chamber membership guide | Classic $400; Leader $6,000 | https://www.tricityregionalchamber.com/uploads/4/8/9/6/48961239/oct_2025_membership_investment_guide_-_smaller.pdf |
| Tri-City Regional Chamber sponsorship notice | Exclusive examples at $6,000 and $10,000 | https://www.tricityregionalchamber.com/blog/sponsorship-opportunities-be-the-face-of-two-high-impact-events |
| Pasco Chamber sponsorship packet | Agriculture and program examples from $1,900 to $6,000 | https://pascochamber.org/wp-content/uploads/2025/04/2025-SPONSORSHIP-PACKET-2.pdf |
| Richland Chamber Cool Desert Nights | Fan sponsorship listed at $500; committee, vendor and volunteer activation available | https://www.richlandchamber.org/cool-desert-nights/ |
| West Richland Veterans Day Parade | Sponsor, volunteer and parade-entry opportunities; pricing requires organizer confirmation | https://westrichlandchamber.org/event/26th-annual-tri-cities-regional-veterans-day-parade-2/ |

# Appendix D. Calendar Control Rule

The source workbook remains the 100-event research library. The 30-event table in Section 7 is the proposed 2027 operating calendar. Research-library events not selected for 2027 remain available for future-year planning, replacements caused by cancellation, or Chief Editor-directed changes. Any substitution requires a written reason and approval before the integrated calendar changes.