CONTROLLED ENTERPRISE DOCUMENT TBT-01.07 ¦ Subcontractor Site Coordination And Stacking MH Construction, INC Enterprise Management System Document family: TOOLBOX TALK LIBRARY Document title: TBT-01.07 ¦ Subcontractor Site Coordination And Stacking Version: 1.0 ¦ Lifecycle: Rough Draft Use only after required functional, technical, field-usability, and approval gates are complete.

Control: Version 1.0 | Status Rough Draft | Author and Chief Editor: Matt Ramsey | Co-Editor: Todd Shoeff | Final Approver: Jeremy Thamert

# TBT-01.07: Subcontractor Site Coordination & Stacking

CSI Division: Div 01 | OSHA Reference: MH Standard

Delivery: Mandatory for all Superintendents and Foremen managing multi-trade sites.

## DIRECTIVE — Policy Standard

Trade stacking (multiple subcontractors working in the same vertical or horizontal space) is prohibited unless specifically authorized by the MH Superintendent with a coordinated JHA.

### GENERAL ORDER — Procedure

The MH Foreman must sequence work so that overhead trades (e.g., ironworkers, electricians) are not working directly above ground-level trades (e.g., plumbers, concrete finishers).

### Key Hazards & Mitigation (The 'What If'):

• Dropped Objects: If an electrician is working on a scissor lift above a plumbing crew, a dropped tool becomes a fatal projectile. The area below the lift must be barricaded with red danger tape.

• Chemical Exposure: If painters are applying solvent-based coatings in the same room where welders are working, the fumes create a fire hazard. Sequence the hot work before the painting.

• Egress Blocking: If the drywall delivery blocks the primary exit corridor while the framing crew is working inside, stop the delivery. Maintain clear egress at all times.

#### FIELD INSTRUCTION — Execution

FIELD INSTRUCTION: Foremen must review today's trade schedule and physically verify that no crews are stacked vertically. Update MISH-F-09.2 (JHA) to reflect coordination. Log attendance on MISH-F-10.1.

Attendance Roster (Log on MISH-F-10.1):

| Print Name | Signature | Company/Trade |
| --- | --- | --- |